This form is for use for both CTIMPs and non-CTIMPS.

Refer to CCTU/SOP004 (CTIMPs) or CCTU/SOP077 (non-CTIMPs) before completing the form.

| IRAS ID |  | CCTU No |  |
| --- | --- | --- | --- |
| LPLV at all participating sites: |  |  |  |

The following tasks must be completed following LPLV and completion of all trial related activities as per protocol in all UK and non-UK sites.

| Task | Relevant documention | Date completed | Who is responsible | Comments |
| --- | --- | --- | --- | --- |
| Trial Coordination |  |  |  |  |
| End of Trial Declaration form completed | For trials submitted through combined review the EoT declaration Form is available within IRAS For trials not submitted through combined review the EoT form is available from MHRA website |  | CTC/CI |  |
| For CTIMPS: EoT Declaration form sent to CCTU regulatory team for review. Non-CTIMPS: EoT Declaration form sent to SCTC/CTM for review |  |  | CTC/CCTU regulatory team CTC |  |
| End of Trial Declaration submitted to REC and MHRA | For trial submitted via combined review, the EoT declaration form is submitted via IRAs and automatically goes to both REC and MHRA For trials not submitted via combined review the EoT declaration form is submitted separately to REC and MHRA |  | CTC |  |
| Acknowledgments of EoT declaration received from REC/HRA/MHRA and filed in TMF |  |  | CTC |  |
| Declaration of EoT form and acknowledgments sent to CUH R&D and to all participating sites for inclusion in their ISF. |  |  | CTC |  |
| Inform funder of EoT and complete any end of trial reports as required | As per funder instructions |  | CTC/CI |  |
| Inform labs, collaborators, and other interested parties of trial end |  |  | CTC |  |
| Inform clinical trial registries (e.g. ISRCTN, clinicaltrialsgov) of trial closure and complete their records | CCTU/GD059 |  | CTC |  |
| Ensure CPMS records updated, ReDA is updated, all trial websites are updated |  |  | CTC |  |
| Complete filing of documentation in TMF | CCTU/SOP015 |  | CTC |  |
| Check and complete TMF files kept separate (e.g. DMF, Stats File, Pharmacy etc) Ensure all collected to be archived together. | CCTU/SOP015 CCTU/TPL032 CCTU/TPL063 CCTU/TPL058 |  | CTC, DM, statistician, pharmacist |  |
| Data Management |  |  |  |  |
| All CRFs received from all participating sites |  |  | CTC/DM |  |
| All data queries resolved from all participating sites |  |  | CTC/DM |  |
| All SAEs received from sites, queries resolved, DB updated, |  |  | CTC/DM |  |
| Data cleaning completion, QA activities completed as per trial DMP | CCTU/SOP060 CCTU/TPL009 |  | DM/SDM/CTC |  |
| SAP finalised | CCTU/TPL007 |  | statistician |  |
| DB softlock | CCTU/FRM097 |  | programmers |  |
| Final data queries resolved and DB hard lock | CCTU/FRM097 |  | CTC/DM/statistician/ programmers |  |
| Randomisation system closed and data downloaded and unblinded (if appropriate) | CCTU/FRM045 |  | CTC/programmer |  |
| Trial sample management |  |  |  |  |
| Collection, storage and/or destruction of all trial samples from sites | CCTU/SOP044 |  | CTC |  |
| Samples analysis planned/completed or samples stored/transferred to another study as per trial protocol and IRAS | CCTU/SOP044 |  |  |  |
| Trial Monitoring |  |  |  |  |
| For CTIMPS: Arrange a close-out visit for the lead site (CUH) | CCTU/SOP011 CCTU/TPL069 |  | CTC/CCTU monitors |  |
| Completion of close-out monitoring reports from all participating sites (to include IMP accountability, archiving arrangements, final PNC log, delegation log, long term responsibilities etc) | CCTU/TPL099 CCTU.TPL069 CCTU/SOP011 CCTU/GD008 |  | CTC |  |
| Confirm resolution of all outstanding monitoring findings and that all PNCs resolved and recorded on central PNC log |  |  | CTC |  |
| Pharmacy/IMP |  |  |  |  |
| Complete IMP accountability |  |  |  |  |
| Instruct sites to destroy any unused/expired IMP (if appropriate) |  |  |  |  |
| End of Trial Reports |  |  |  |  |
| Prepare Final results report for submission within 1 year of end of trial date. - For trials submitted through combined review, report can be generated/submitted within IRAS - For trials not submitted through combined review, the report is submitted via an online form | IRAS HRA online form |  | CTC |  |
| Acknowledgment of receipt Final Report from REC/HRA and pdf of Final Report filed in TMF |  |  | CTC |  |
| Provide End of Trial Report pdf and REC/ HRA acknowledgment to CCTU regulatory team (CTIMPS), CUH R&D, and to all participating sites for filing in their ISF. |  |  | CTC |  |
| For CTIMPS: Prepare the End of Trial Summary results for the MHRA within 1 year of end of trial and send to regulatory and CI for review | EudraCT online form | CCTU/GD059 | CI/CTC/statisticians/ regulatory team |  |
| Within 15 days of the EudraCT summary of results submission inform the MHRA |  |  | CTC |  |
| The data set posted and confirmatory email to MHRA will be: - Filed in TMF - Sent to CCTU regulatory team - Send to participating sites for filing in the ISF |  |  | CTC |  |
| Close out of sites and archiving |  |  |  |  |
| Close out all participating sites | Complete Form 117B for each site |  | CTC |  |
| Sponsors end of trial confirmation letter received and filed in TMF |  |  | CCTU/regulatory or director of operations |  |
| Make arrangements for the archiving of trial related documentation (TMF and related files, pCRFs etc) at the lead site | CCTU/SOP006 |  |  |  |
| Financial |  |  |  |  |
| Ensure all invoices from: sites, labs, CCTU, collaborators, IMP manufacturers/distributors ect paid before grant closes. |  | CTC |  |  |
| Close cost code, liaise with R&D finance for the preparation and submission of FSTOX to funder |  | CTC/CI |  |  |
| Publications |  |  |  |  |
| Assist CI with any publications and send copies to CCTU inbox |  |  | CTC, CI, statisticians |  |

Acronyms used:

DM = Data Manager

SDM = Senior Data Manager

CTM = Clinical Trials Manager

SCTC = Senior Clinical Trials Manager

CTC = Clinical Trails Coordinator

DMF= Data Management File

Name and title of person completing this form:

Date: