This form is for use for both CTIMPs and non-CTIMPS.

Refer to CCTU/SOP004 (CTIMPs) or CCTU/SOP077 (non-CTIMPs) before completing the form.

Please select appropriate blue text and ensure all text is black prior to completing the form

| IRAS ID |  | CCTU No |  |
| --- | --- | --- | --- |
| LPLV at all participating sites: |  |  |  |

The following tasks must be completed following LPLV and completion of all trial related activities as per protocol in all UK and non-UK sites.

| Task | Relevant documentation | Date completed | Who is responsible | Comments |
| --- | --- | --- | --- | --- |
| Trial Coordination |  |  |  |  |
| End of Trial Declaration Form completed within required timelines | For CTIMP trials submitted through combined review the EoT declaration Form is available within IRAS For CTIMP trials not submitted through combined review the EoT form is available from MHRA website For Non-CTIMPs the EoT form is available to download from the HRA website |  | CTC/CI |  |
| For CTIMPS: EoT Declaration form sent to CCTU regulatory team for review. Non-CTIMPS: EoT Declaration form sent to SCTC/CTM for review |  |  | CTC/CCTU regulatory team CTC |  |
| End of Trial Declaration submitted to REC and MHRA | For CTIMP trials submitted via combined review, the EoT declaration form is submitted via IRAs and automatically goes to both REC and MHRA For CTIMP trials not submitted via combined review the EoT declaration form is submitted separately to REC and MHRA For CTIMPs a copy must be provided to the Regulatory Team for the Sponsor File For non-CTIMPs, the completed EoT form is emailed to the REC |  | CTC |  |
| Acknowledgments of EoT declaration received from REC/HRA/MHRA and filed in TMF |  |  | CTC |  |
| Declaration of EoT form and acknowledgments sent to CUH R&D and to all participating sites for inclusion in their ISF. |  |  | CTC |  |
| Inform funder of EoT and complete any end of trial reports as required | As per funder instructions |  | CTC/CI |  |
| Inform labs, collaborators, and other interested parties of trial end |  |  | CTC |  |
| Inform clinical trial registries (e.g. ISRCTN, clinicaltrialsgov) of trial closure and complete their records | CCTU/GD059 |  | CTC |  |
| Ensure CPMS records updated, ReDA is updated, all trial websites are updated |  |  | CTC |  |
| Pharmacy/IMP |  |  |  |  |
| Complete IMP accountability from all sites as required |  |  |  |  |
| Instruct sites to destroy any unused/expired IMP (if appropriate) |  |  |  |  |
| Complete close-out monitoring of site pharmacy |  |  |  |  |
| Data Management |  |  |  |  |
| All data/CRFs received from all participating sites, all data entered into trial database |  |  | CTC/DM/DS |  |
| All data queries resolved from all participating sites |  |  | CTC/DM/DS |  |
| All SAEs received from sites, queries resolved, DB updated |  |  | CTC/DM/DS |  |
| Complete final PV reconciliation and file final End of Trial Safety Line Listing from PV in the TMF |  |  | CTC/PV manager |  |
| Data cleaning completion, data entry verification and QA activities completed - as per trial DMP | CCTU/SOP089 CCTU/TPL009 |  | DM/DS/SDM/CTC |  |
| Ensure all pCRFs/e-CRFs requiring PI/CI sign-off at the end of trial are completed (eg AE Log, Con-Med Log etc) prior to DB Softlock |  |  | DM/SDM |  |
| SAP finalised | CCTU/TPL007 |  | statistician |  |
| DB softlock | CCTU/FRM097 |  | programmers |  |
| Final data queries resolved and DB hard lock | CCTU/FRM097 |  | CTC/DM/statistician/ programmers |  |
| Randomisation system closed and data downloaded and unblinded (if appropriate) | CCTU/FRM045 |  | CTC/programmer |  |
| Trial sample management |  |  |  |  |
| Collection of all samples from sites and stored appropriately (if applicable) | CCTU/SOP044 (Records of sample collection from sites e.g. sample collection logs from sites) |  | CTC |  |
| Samples analysis planned/completed or samples stored/transferred to another study as per trial protocol and IRAS or samples destroyed | CCTU/SOP044 (complete appropriate documentation to indicate what is happening with samples) |  | CTC |  |
| Inform CCTU QA Manager of completion of lab activities for the trial |  |  |  |  |
| Trial Monitoring and close out of sites |  |  |  |  |
| For CTIMPS: Arrange close-out visits for all sites as per trial Monitoring For non-CTIMPs arrange a close out monitoring visit for all sites | CCTU/SOP011 CCTU/TPL069 CCTU/TPL069 |  | CTC/CCTU monitors |  |
| Completion of close-out monitoring reports from all participating sites (to include IMP accountability, archiving arrangements, final NC log, delegation log, long term responsibilities etc) | CCTU/TPL099 CCTU/TPL069 CCTU/SOP011 CCTU/GD008 |  | CTC |  |
| Confirm resolution of all outstanding monitoring findings and that all NCs resolved and recorded on central NC log |  |  | CTC |  |
| Close out all participating sites | Complete Form 117B for each site |  |  |  |
| End of Trial Reports |  |  |  |  |
| Prepare Final results report for submission within 1 year of end of trial date. | IRAS/HRA online form For trials submitted through combined review, report can be generated/submitted within IRAS For trials not submitted through combined review, the report is submitted via an online form |  | CTC |  |
| Acknowledgment of receipt Final Report from REC/HRA and pdf of Final Report filed in TMF |  |  | CTC |  |
| Provide End of Trial Report pdf and REC/ HRA acknowledgment to CCTU regulatory team (CTIMPS), CUH R&D, and to all participating sites for filing in their ISF. |  |  | CTC |  |
| Upload the results to ISRCTN or equivalent and inform the MHRA via email of its completion within 1 year of the end of trial date |  |  | CTC |  |
| For CTIMPS, The data set posted and confirmatory email to MHRA will be: - Filed in TMF - Sent to CCTU regulatory team - Sent to participating sites for filing in the ISF |  |  | CTC |  |
| TMF check and archiving |  |  |  |  |
| Sponsors end of trial confirmation letter received and filed in TMF |  |  | CCTU/regulatory or Director of Operations |  |
| Complete filing of all trial documentation in TMF | CCTU/SOP015 CCTU/TPL032 |  | CTC, DM, statistician, pharmacist |  |
| Final monitoring of TMF completed |  |  |  |  |
| Check and complete TMF files kept separate (e.g. DMF, Stats File, Pharmacy etc) Ensure all collected to be archived together. | CCTU/TPL034 CCTU/TPL056 CCTU/TPL080 |  | CTC, DM, statistician, pharmacist |  |
| Make arrangements for the archiving of trial related records (TMF and related files, pCRFs etc) at the lead site | CCTU/SOP006 |  | CTC |  |
| Trial result dissemination |  |  |  |  |
| Lay summary of results prepared and send to sites for their participants |  |  |  |  |
| Lay summary published in trial website or other public database |  |  |  |  |
| Financial |  |  |  |  |
| Ensure all invoices from: sites, labs, CCTU, collaborators, IMP manufacturers/distributors etc paid before grant closes. |  | CTC |  |  |
| Close cost code, liaise with R&D finance for the preparation and submission of FSTOX (final financial statement of expenditure) to funder |  | CTC/CI |  |  |
| Publications |  |  |  |  |
| Assist CI with any publications and send copies to CCTU inbox |  |  | CTC, CI, statisticians |  |
| Ensure any/all MHRA reported serious breaches are included in the publications |  |  | CTC/CI/ Statisticians |  |
| Ensure CCTU is appropriately acknowledged in publications |  |  | CTC/CI/ Statisticians |  |

Acronyms used:

DM = Data Manager

DS = Data Specialist (for cancer theme)

SDM = Senior Data Manager

CTM = Clinical Trials Manager

SCTC = Senior Clinical Trials Manager

CTC = Clinical Trails Coordinator

DMF= Data Management File

| Name and title of person completing this form: |  |
| --- | --- |
| Date: |  |